## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
1 | FS 1 / Req_1 | Admin Registration | As an admin, I want to open admin registration page and save the entered admin details. | Task #1 | Project setup and configuration and access to Login/Registration Page | Critical | Shrey | 18/3/19 | 19/3/19 | 6 | M | Completed | The objective of this requirement is to allow the admin to Register as a new admin and redirect to login form. | Admin being able to access the loginpage & get redirected to the ‘Sign up’ page upon click of ‘Join us’ link. | Scrum Master | Average | High | New Requirement
|  |  |  | Task #2 | Create Login JSP page | Critical | Shrey | 19/3/19 | 20/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #3 | Field Validations on Login JSP | Critical | Deepankar | 20/3/19 | 21/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #4 | Create a Registration JSP page to accept the data from Admin as per the field of Login table. | Medium | Punit | 21/3/19 | 22/3/19 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #5 | Create Login class, Login DAO and Login Service class to insert the admin data and controller and verify on backend. | Critical | Punit | 22/3/19 | 23/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #6 | Integrate the code and verify its working . | Medium | Deepankar | 24/3/19 | 24/3/19 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
2 | FS 2 / Req_2 | Admin Authentication | As an admin, I want to enter the details for log-in and the credentials get authenticated. | Task#1 | Create the Authenticate function in Login dao , Login service and call the function in the Login controller. | High | Shrey | 25/3/19 | 31/3/19 | 6 | M | Completed | The objective of this requirement is to authenticate the details of admin and redirect to viewInventory page. |  | Scrum Master | Average | High | New Requirement
3 | FS 3 / Req_3 | Add Inventory | As an admin, I want to add the details of inventory and get redirected to the "viewInventory" page. | Task#1 | Create addInventory JSP page to enter the details of inventory. | Critical | Deepankar | 2019-01-04 | 2019-01-04 | 6 | M | Completed | The objective of this requirement is to add the details of inventory. | Admin being able to access the loginpage & get redirected to the ‘viewInventory’ page upon successful authentication. | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Field Validations on addInventory JSP page. | Critical | Punit | 2019-02-04 | 2019-02-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | Create viewInventory JSP page. | Medium | Shrey | 2019-03-04 | 2019-03-04 | 6 | S | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#4 | Create Inventory class, Inventory dao and Inventory Service class to insert the inventory data and controller and verify on backend. | Critical | Shrey | 2019-04-04 | 2019-04-04 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#5 | Integrate the code and verify its working . | Medium | Deepankar | 2019-05-04 | 2019-05-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
4 | FS 4 / Req_4 | Add Restaurant Staff | As an admin, I want to add the details of staff and get redirected to the "viewStaff" page. | Task#1 | Create addStaff JSP page to enter the details of staff. | Critical | Punit | 2019-06-04 | 2019-06-04 | 6 | S | Completed | The objective of this requirement is to add the details of staff. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Field Validations on addStaff JSP page. | Medium | Punit | 2019-07-04 | 2019-07-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | Create viewStaff JSP page. | Medium | Deepankar | 2019-08-04 | 2019-08-04 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#4 | Create Staff class, Staff dao and Staff Service class to insert the staff data and controller and verify on backend. | Critical | Deepankar | 2019-09-04 | 2019-09-04 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#5 | Integrate the code and verify its working . | Low | Shrey | 2019-10-04 | 2019-10-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
5 | FS 5 / Req_5 | Inventory Maintenance | As an admin, I want to see the data of the inventory and edit the detaills. | Task#1 | Add function to fetch the data from the database in Inventory dao,call the function in the service and call the service in the inventory controller. | Critical | Shrey | 2019-11-04 | 13/4/2019 | 6 | L | Completed | The objective of this requirement is to see the data of inventory and also let the admin to edit/delete the details of inventory. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Add function to update the data in the database in Inventory dao,call the function in the service and call the service in the inventory controller. | Critical | Deepankar | 13/4/2019 | 15/4/2019 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement